## Sheet1
Case Number | Customer Name | Task Name | Project | Main Module | Sub Module | Developer | Work Type | Priority | Status | Start Date | End Date | Est Hrs | Actual Hrs | % Complete | Duration (d) | Sprint (Start) | Cross-Month? | Cross-Module? | Customer Committed? | Remaining Hrs | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | Filter Match | Filter Rank | Data Issues (auto)
Internal | Internal | TLG Credit note and other changes | FX POS | FX POS | Configuration | Jhansi Nadella | New Requirement | Medium | Completed | 2026-07-01 | 2026-07-03 |  |  | 100% | 3 | Jul-2026 | No | No | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 149
Internal | Internal | fx-pos reports, pos paramer project configure | FX POS | FX POS | Configuration | Lakmali Vithanalage | New Requirement | Low | Completed | 2026-07-09 | 2026-07-09 | 8 |  | 100% | 1 | Jul-2026 | No | No | Yes | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 150
Internal | Internal | Room Restriction Settlement changes for In House Guest | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-07-02 | 2026-07-02 | 9 | 9 | 100% | 1 | Jul-2026 | No | No | No | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 151
Internal | Internal | FX/FN Steward App Remove pax count field in open table | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-07-01 | 2026-07-01 | 6 | 4 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 152
Internal | Internal | FX/FN Steward App Tax exemption reason capture UI and API parameter changes | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-07-02 | 2026-07-02 | 8 | 8 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 153
Internal | Internal | FX Steward App HSN/SAC field introduced in open item | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-07-03 | 2026-07-03 | 4 | 4 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 154
Internal | Internal | FX Steward App Open Item IsDiscountAllowed default tick mark selection added | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-07-03 | 2026-07-03 | 4 | 4 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 155
Internal | Internal | FX Steward App Settlement API request changes | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Internal Issue | Medium | Completed | 2026-07-06 | 2026-07-06 | 7 | 7 | 100% | 1 | Jul-2026 | No | Yes | No | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 156
Internal | Internal | FX Steward App Tax exemption for split issue fixing | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Internal Issue | Medium | Completed | 2026-07-07 | 2026-07-09 | 24 | 22 | 100% | 3 | Jul-2026 | No | Yes | No | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 157
Internal | Internal | FX/FN Steward App Account date and time should show in order confirmation pop up | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-07-10 | 2026-07-10 | 3 | 3 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 158
1424211 | Airways Hotel & Aptments; Papua New Guinea | In Same KOT different table number should not write (extra Validation ) | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | Medium | QA-Staging | 2026-07-13 | 2026-07-15 | 24 | 15 | 80% | 3 | Jul-2026 | No | No | No | 5 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 159
Internal | Internal | Table # empty writing in KOT Detail table | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | Medium | QA-Staging | 2026-07-13 | 2026-07-15 | 24 | 20 | 80% | 3 | Jul-2026 | No | No | No | 5 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 160
1387164 | SHUROOQ LIMITED T/A MAJESTIC HOTEL CARDIFF; UK | POS Card Settlement not reflecting in FX ACR and Journal entries | FX POS | FX POS | Order entry | Jhansi Nadella | Production Issue | Medium | QA-Staging | 2026-07-01 | 2026-07-07 | 40 | 35 | 85% | 7 | Jul-2026 | No | No | Yes | 6 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 1 | 161
Internal | Internal | Deposit API | FX POS | FX POS | Order Entry | Jhansi Nadella | New Requirement | High | QA-WIP | 2026-07-07 | 2026-07-17 | 56 | 45 | 50% | 11 | Jul-2026 | No | No | Yes | 28 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 1 | 162
Internal | Internal | Room posting extra Validation Guest reference/Guest reg no/Room no etc.. in KOT save and Settlement | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | QA-WIP | 2026-07-01 | 2026-07-02 | 16 | 10 | 100% | 2 | Jul-2026 | No | No | No | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 163
Internal | Internal | Local Storage Encryption Changes | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | High | QA-WIP | 2026-07-03 | 2026-07-13 | 65 | 20 | 90% | 11 | Jul-2026 | No | No | Yes | 7 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 1 | 164
1391040 | Water Edge Srilanka | Need to collect advances from FX Point of Sales Module | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | High | QA-WIP | 2026-07-01 | 2026-07-17 | 96 | 80 | 50% | 17 | Jul-2026 | No | No | Yes | 48 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 1 | 165
Internal | Internal | Outlet name change-Tax struture not loaded in Menu item | FX POS | FX POS | Configuration | Sumanth Syam Kantipalli | Internal Issue | Medium | QA-Staging | 2026-07-01 | 2026-07-03 | 24 | 20 | 100% | 3 | Jul-2026 | No | No | No | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 166
Internal | Internal | If new Outlets created, Active Online, Active Delivery , QSR written as NULL instead of 0.-Rahul & Sumanth | FX POS | FX POS | Configuration | Sumanth Syam Kantipalli | Internal Issue | Medium | QA-Staging | 2026-07-03 | 2026-07-06 | 12 | 10 | 100% | 4 | Jul-2026 | No | No | No | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 167
1312809 | Airways Hotel & Aptments; Papua New Guinea | Menu audit log report | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | High | QA-Staging | 2026-07-06 | 2026-07-10 | 40 | 35 | 100% | 5 | Jul-2026 | No | No | Yes | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 1 | 168
Internal | Internal | Advance report in POS sales 7 reports | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | Medium | QA-WIP | 2026-07-13 | 2026-07-16 | 32 | 30 | 50% | 4 | Jul-2026 | No | No | Yes | 16 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 169
1434771 | Al Feyhaa Resthouse Oman | Shift end report-Based up on Hotel info qty,decimal places | FX POS | FX POS | Reports | Swarnalatha Bairava Mohan | Internal Issue | Medium | QA-Staging | 2026-07-06 | 2026-07-09 | 32 | 25 | 100% | 4 | Jul-2026 | No | No | No | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 170
1346644 | Sentrim Amboseli Lodge; Kenya | Integration with Kopo kopo Gateway-API | FX POS | FX POS | Settlement | Swarnalatha Bairava Mohan | New Requirement | High | QA-WIP | 2026-07-02 | 2026-07-09 | 48 | 35 | 80% | 8 | Jul-2026 | No | No | Yes | 10 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 1 | 171
NA | Brigade Group | Realtime Integration with FN CMS | FX POS | FX POS | Settlement | Swarnalatha Bairava Mohan | New Requirement | High | QA-WIP | 2026-07-10 | 2026-07-21 | 56 | 50 | 80% | 12 | Jul-2026 | No | No | Yes | 11 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 1 | 172
Internal | Internal | FX Steward App Generate and print bill, email split bills, WhatsApp split bills issue fixings | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Internal Issue | Medium | Completed | 2026-07-13 | 2026-07-16 | 30 | 28 | 100% | 4 | Jul-2026 | No | Yes | No | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | 174
Internal | Internal | Discount % -Validation should not allow more than 100 | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | Medium | Not Started | 2026-07-15 | 2026-07-17 |  |  |  | 3 | Jul-2026 | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 175
Internal | Internal | Pick from other outlet l, sales should go to that outlet only due to license liquor lssues | FX POS | FX POS | Order Entry | Jhansi Nadella | New Requirement | High | Not Started | 2026-07-27 | 2026-07-31 |  |  |  | 5 | Jul-2026 | No | No | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 176
Internal | Internal | Direct login remove from POS | FX POS | FX POS | Configuration | Rashmi Kumari | Internal Task | High | QA-WIP | 2026-07-20 | 2026-07-22 | 24 | 24 | 100% | 3 | Jul-2026 | No | No | No | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 177
1425715 | Mirai Restaurant Mumbai | KOT reprint in FX POS | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | High | QA-WIP | 2026-07-14 | 2026-07-17 | 8 | 8 | 100% | 4 | Jul-2026 | No | No | Yes | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 178
Internal | Internal | Code and project architecture modifications for ordering | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Tech Upgrade | Medium | Completed | 2026-07-17 | 2026-07-20 | 16 | 16 | 100% | 4 | Jul-2026 | No | Yes | No | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 182
Internal | internal | POS communicator new exe cause of AWS | FX POS | FX POS | Bill Print | Ankit Mishra | New Requirement | High | Completed | 2026-06-18 | 2026-06-25 | 48 | 48 | 100% | 8 | Jun-2026 | No | Yes | Yes | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 393
Internal | Internal | Liaison KOT changes | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | High | Completed | 2026-06-04 | 2026-06-06 | 20 | 16 | 100% | 3 | Jun-2026 | No | No | Yes | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 394
Internal | Internal | cityledger settlement staff printing issue | FX POS | FX POS | Bill Print | Devana Jagadeesh | Internal Issue | Medium | Completed | 2026-06-11 | 2026-06-11 | 6 | 4 | 100% | 1 | Jun-2026 | No | No | No | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 395
Internal | internal | Guest Name related Chnages | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | Medium | Completed | 2026-06-12 | 2026-06-12 | 2 | 4 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 396
Internal | Internal | Dragon format multiple changes | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | Medium | Completed | 2026-06-12 | 2026-06-12 | 8 | 6 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 397
NA | TLG Portugal | Bill pringt format changes | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | Medium | Completed | 2026-06-17 | 2026-06-17 | 4 | 3 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 398
Internal | Internal | Liaison Relay changes | FX POS | FX POS | Bill Print | Devana Jagadeesh | Internal Issue | Medium | Completed | 2026-06-18 | 2026-06-18 | 4 | 2 | 100% | 1 | Jun-2026 | No | No | No | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 399
Internal | Internal | old pos communicator created for properties due to new relay | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | High | Completed | 2026-06-19 | 2026-06-25 | 40 | 40 | 100% | 7 | Jun-2026 | No | No | Yes | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 400
Internal | Internal | Print realted Footer , remarks , till number changes | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | High | Completed | 2026-06-25 | 2026-06-25 | 8 | 6 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 401
NA | Karan Sharq Hotel Apartments Co; | Vat % related change | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | High | Completed | 2026-06-26 | 2026-06-26 | 4 | 6 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 402
NA | Sentrim Hotel | New liaosn setup and exe craeted | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | Medium | Completed | 2026-06-26 | 2026-06-26 | 4 | 6 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 403
Internal | Internal | procedure issue with AWS settlement details not printing and reprint not happening for POS communicator | FX POS | FX POS | Bill Print | Devana Jagadeesh | Production Issue | High | Completed | 2026-06-26 | 2026-06-27 | 16 | 12 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 404
NA | Sentrim Hotel | Bill and settlement copy printing issue | FX POS | FX POS | Bill Print | Devana Jagadeesh | Internal Issue | High | Completed | 2026-06-30 | 2026-06-30 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 405
Internal | Internal | Footer changes in Liaison Bill copy | FX POS | FX POS | Bill Print | Devana Jagadeesh | New Requirement | Medium | Completed | 2026-06-30 | 2026-06-30 | 4 | 2 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 406
NA | TLG Portugal | Revenue Tax Exemption changes | FX POS | FX POS | Order Entry | Indira Priyadharshini | New Requirement | High | Completed | 2026-06-12 | 2026-06-23 | 16 | 12 | 100% | 12 | Jun-2026 | No | Yes | Yes | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 407
1341002 | Oak WLL Bharain | 3 Decimal places issues with Amount Discount | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | High | Completed | 2026-06-01 | 2026-06-03 | 32 | 24 | 100% | 3 | Jun-2026 | No | No | No | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 408
Internal | Internal | Double posting issue - Transfer programs | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | High | Completed | 2026-06-04 | 2026-06-04 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 409
Internal | Internal | POS Tax Table deletion Issues | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | High | Completed | 2026-06-04 | 2026-06-04 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 410
Internal | Internal | Happy hour Transfer Program chnages need to deploy to all db | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | High | Completed | 2026-06-05 | 2026-06-05 | 8 | 8 | 100% | 1 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 411
NA | Canza Certification | Improper Input Validation Leading to Fail-Open Response Behavior | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-08 | 2026-06-08 | 8 | 8 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 412
NA | Canza Certification | OTP Brute-Force Leading to Account Takeover | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-09 | 2026-06-09 | 8 | 8 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 413
NA | Canza Certification | OTP Brute-Force Vulnerability Leading to Account Takeover in Production | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-10 | 2026-06-10 | 8 | 8 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 414
NA | Canza Certification | Hardcoded Database Connection String Exposed in JWT Token via Cookie Header | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-11 | 2026-06-11 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 415
NA | Canza Certification | Improper Validation of OAuth 2.0 Grant Type Parameter | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-11 | 2026-06-12 | 12 | 12 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 416
NA | Canza Certification | Improper OAuth Grant Type Validation in Production Authentication Endpoint | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-15 | 2026-06-15 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 417
NA | Canza Certification | Publicly Accessible Swagger API Documentation in Production and Staging Environments | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-15 | 2026-06-16 | 4 | 4 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 418
NA | Canza Certification | User Enumeration via Differential Response Leading to Account Takeover Risk (Broken Access Control) | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-16 | 2026-06-16 | 8 | 4 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 419
NA | Canza Certification | Session Management Failure — Access Token Not Invalidated After Logout | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-16 | 2026-06-17 | 12 | 12 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 420
NA | Canza Certification | Missing Authentication Validation Across Multiple API Endpoints | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-18 | 2026-06-19 | 16 | 12 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 421
NA | Canza Certification | Broken Authentication & Access Control Leading to Mass Data Exposure | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-19 | 2026-06-22 | 22 | 20 | 100% | 4 | Jun-2026 | No | No | Yes | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 422
NA | Canza Certification | Improper Authentication on Email Service API Leading to Email Abuse | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-22 | 2026-06-23 | 10 | 10 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 423
NA | BSecure Certication | Error-Based SQL Injection in List by Login API | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-24 | 2026-06-24 | 8 | 6 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 424
NA | BSecure Certication | Verbose Error Message in Reset Password API | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-24 | 2026-06-24 | 6 | 2 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 425
NA | BSecure Certication | No Rate Limiting on Change Password Functionality | FX POS | FX POS | Admin | Jhansi Nadella | New Requirement | High | Completed | 2026-06-25 | 2026-06-25 | 8 | 8 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 426
Internal | Internal | TLG SAF T File Changes-BillFormat,Required xml tags data bind | FX POS | FX POS | Settlement | Jhansi Nadella | New Requirement | Medium | Completed | 2026-06-26 | 2026-06-27 | 8 | 16 | 100% | 2 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 427
Internal | Internal | FXPOS -Configuration Changes Azure to AWS | FX POS | FX POS | Configuration | Jhansi Nadella | New Requirement | High | Completed | 2026-06-29 | 2026-06-29 | 2 | 2 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 428
Internal | Internal | Tax excemption during KOTSave and BillProcess except | FX POS | FX POS | Order Entry | Jhansi Nadella | Internal Issue | Medium | Completed | 2026-06-29 | 2026-06-30 | 12 | 12 | 95% | 2 | Jun-2026 | No | No | No | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 429
Internal | Internal | TAX not calculating on open Modifier Items value | FX POS | FX POS | Order Entry | Lakmali Vithanalage | Internal Issue | High | Completed | 2026-06-02 | 2026-06-10 | 60 | 50 | 100% | 9 | Jun-2026 | No | No | No | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 430
NA | Water Edge Srilanka | Happy Hours auto refresh once time starts, Happy Hours rates will be picked up | FX POS | FX POS | Order Entry | Lakmali Vithanalage | Internal Issue | High | Completed | 2026-06-10 | 2026-06-11 | 8 | 5 | 100% | 2 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 431
Internal | Internal | Tax Exemption should calculate once click OK.. Now after generate only showing correct value. | FX POS | FX POS | Order Entry | Lakmali Vithanalage | New Requirement | Medium | Completed | 2026-06-12 | 2026-07-02 | 120 | 100 | 100%% | 21 | Jun-2026 | Yes | No | Yes | 0 | 108.6 | 11.4 | 0 | 0 | 0 | 0 | 0 | 1 | 432
Internal | internal | Opera mapping in parameter | FX POS | FX POS | Configuration | Monika Tiwari | New Requirement | Medium | Completed | 2026-06-01 | 2026-06-04 | 40 | 40 | 100% | 4 | Jun-2026 | No | No | Yes | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 433
1386386 | The Dukes Retreat; Khandala | Decimal places in order entry | FX POS | FX POS | Order Entry | Monika Tiwari | New Requirement | Medium | Completed | 2026-06-05 | 2026-06-08 | 24 | 24 | 100% | 4 | Jun-2026 | No | No | Yes | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 434
Internal | Internal | FX SPA predefined menu group codes produc and services not showing in POS discount master | FX POS | FX POS | Configuration | Monika Tiwari | New Requirement | Medium | Completed | 2026-06-25 | 2026-06-27 | 16 | 16 | 100% | 3 | Jun-2026 | No | No | Yes | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 435
Internal | Internal | Copy pasting more than 45 characters in menu master giving Json Error while creating menu (should restrict ) | FX POS | FX POS | Configuration | Monika Tiwari | Internal Task | Low | Completed | 2026-06-10 | 2026-06-30 | 24 | 24 | 100% | 21 | Jun-2026 | No | No | No | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 436
Internal | internal | Menu Item added reason popup | FX POS | FX POS | Configuration | Monika Tiwari | New Requirement | Medium | Completed | 2026-06-25 | 2026-06-30 | 24 | 24 | 100% | 6 | Jun-2026 | No | No | Yes | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 437
NA | Brigade Group | Fortune Next CMS to FX POS and FX SNC Integration | FX POS | FX POS | Order Entry | Monika Tiwari | New Requirement | High | Completed | 2026-06-01 | 2026-06-30 | 50 | 50 | 100% | 30 | Jun-2026 | No | No | Yes | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 438
Internal | internal | Menu audit report Pos column changes | FX POS | FX POS | Reports | Monika Tiwari | New Requirement | Medium | Completed | 2026-06-02 | 2026-07-02 | 24 | 24 | 100% | 31 | Jun-2026 | Yes | No | Yes | 0 | 22.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 1 | 439
Internal | Internal | Sales by Server report(UI) | FX POS | FX POS | Reports | Rahul Ashish Dsouza | New Requirement | High | Completed | 2026-06-11 | 2026-06-16 | 32 | 32 | 100% | 6 | Jun-2026 | No | No | Yes | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 440
Internal | Internal | Banquet is restricted for Order Entry | FX POS | FX POS | Configuration | Rashmi Kumari | New Requirement | Medium | Completed | 2026-06-01 | 2026-06-01 | 4 | 4 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 441
Internal | Internal | Opera Bill Posting API changes | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-06-01 | 2026-06-01 | 4 | 4 | 100% | 1 | Jun-2026 | No | No | No | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 442
1372718 | The Dukes Retreat; Khandala | Enable cash settlement /Receipt >=200000 | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | Medium | Completed | 2026-06-02 | 2026-06-02 | 4 | 3 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 443
Internal | Internal | Sessions statistics Based up on Outlet access | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-06-03 | 2026-06-03 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 444
Internal | Internal | KOT print required for QSR Outlet type | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-06-04 | 2026-06-04 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 445
Internal | Internal | Modifier screen Sub item Name Add&Amend mode issues | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-05 | 2026-06-05 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 446
Internal | Internal | Reprint bill not happening inside order entry | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-08 | 2026-06-08 | 9 | 5 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 447
Internal | Internal | Manager login api was not working, due to wrong url configuration | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | High | Completed | 2026-06-08 | 2026-06-08 | 1 | 1 | 100% | 1 | Jun-2026 | No | No | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 448
Internal | Internal | In Settlement screen Credit card date Calendar should reflect | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | High | Completed | 2026-06-09 | 2026-06-11 | 27 | 20 | 100% | 3 | Jun-2026 | No | No | No | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 449
Internal | Internal | System to be restricted from punching partial quantities | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-11 | 2026-06-12 | 18 | 15 | 100% | 2 | Jun-2026 | No | No | No | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 450
Internal | Internal | Issue with default settlement option | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-15 | 2026-06-15 | 10 | 10 | 100% | 1 | Jun-2026 | No | No | No | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 451
Internal | Internal | Settlement mode should focus by default Cash-Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | High | Completed | 2026-06-16 | 2026-06-16 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | Yes | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 452
Internal | Internal | Discount % Default selection- Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-17 | 2026-06-17 | 10 | 10 | 100% | 1 | Jun-2026 | No | No | No | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 453
Internal | Internal | Cheque date UI change-Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-18 | 2026-06-18 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 454
Internal | Internal | Settlement screen discount % issues-Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-19 | 2026-06-19 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 455
Internal | Internal | Table Master parameters Takeaway and Open Table showing here-Jhansi & Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-22 | 2026-06-22 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 456
Internal | Internal | HSN Code not writing in KOT Details table.-Jhansi & Rashmi | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Low | Completed | 2026-06-23 | 2026-06-23 | 10 | 10 | 100% | 1 | Jun-2026 | No | No | No | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 457
Internal | Internal | Banquest restricted for order entry | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-06-24 | 2026-06-24 | 1 | 1 | 100% | 1 | Jun-2026 | No | No | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 458
Internal | Internal | Opera Bill Posting Changes | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | Completed | 2026-06-26 | 2026-06-26 | 9 | 9 | 100% | 1 | Jun-2026 | No | No | No | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 459
Internal | Internal | TLG Implementation | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | High | Completed | 2026-06-24 | 2026-07-01 | 50 | 45 | 100% | 8 | Jun-2026 | Yes | No | Yes | 0 | 43.8 | 6.3 | 0 | 0 | 0 | 0 | 0 | 1 | 460
NA | Airways Hotel & Aptments; Papua New Guinea | Loyalty # required in Discount register report(API/Proc) | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | Medium | Completed | 2026-06-01 | 2026-06-03 | 10 | 8 | 100% | 3 | Jun-2026 | No | No | Yes | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 461
Internal | Internal | Sessions statistics Based up on Outlet access | FX POS | FX POS | Order Entry | Sumanth Syam Kantipalli | Internal Issue | Medium | Completed | 2026-06-03 | 2026-06-09 | 5 | 5 | 100% | 7 | Jun-2026 | No | No | No | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 462
Internal | Internal | List bill report issues Demo Item | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | Low | Completed | 2026-06-08 | 2026-06-09 | 6 | 4 | 100% | 2 | Jun-2026 | No | No | No | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 463
Internal | Internal | Sales by Server report(API/Procedure) | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | High | Completed | 2026-06-01 | 2026-06-10 | 32 | 32 | 100% | 10 | Jun-2026 | No | No | Yes | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 464
Internal | Internal | Happy Hours Exclusive condition report changes. | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | High | Completed | 2026-06-09 | 2026-06-12 | 30 | 27 | 100% | 4 | Jun-2026 | No | No | No | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 465
NA | Dragon Beach Resort | Discount option screen freezes | FX POS | FX POS | Configuration | Sumanth Syam Kantipalli | Internal Issue | High | Completed | 2026-06-03 | 2026-06-15 | 16 | 16 | 100% | 13 | Jun-2026 | No | No | No | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 466
Internal | Internal | Bill Cancelled/Void Settlement Report Issue | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | High | Completed | 2026-06-15 | 2026-06-17 | 6 | 6 | 100% | 3 | Jun-2026 | No | No | No | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 467
Internal | Internal | Order Analysis by Time report changes-Sumanth | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | Low | Completed | 2026-06-17 | 2026-06-18 | 8 | 8 | 100% | 2 | Jun-2026 | No | No | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 468
NA | Sentrim Hotel | MMS Point changes with Modifiers | FX POS | FX POS | Configuration | Sumanth Syam Kantipalli | New Requirement | High | Completed | 2026-06-05 | 2026-06-22 | 20 | 20 | 100% | 18 | Jun-2026 | No | No | Yes | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 469
NA | Sentrim Hotel | MMS changes | FX POS | FX POS | Order Entry | Sumanth Syam Kantipalli | New Requirement | High | Completed | 2026-06-05 | 2026-06-22 | 80 | 110 | 100% | 18 | Jun-2026 | No | No | Yes | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 470
Internal | Internal | Bill cancel report- reason code need to update-Sumanth | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | Low | Completed | 2026-06-19 | 2026-06-23 | 20 | 20 | 100% | 5 | Jun-2026 | No | No | No | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 471
Internal | Internal | User role-Member Account & Settlement need to add in all properties-Sumanth | FX POS | FX POS | Order Entry | Sumanth Syam Kantipalli | Internal Issue | Low | Completed | 2026-06-23 | 2026-06-24 | 2 | 2 | 100% | 2 | Jun-2026 | No | No | No | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 472
Internal | Internal | Discount register report changes-Sumanth | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | Internal Issue | High | Completed | 2026-06-24 | 2026-06-29 | 40 | 37 | 100% | 6 | Jun-2026 | No | No | No | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 473
NA | Brigade Group | Club App to FX POS Take away outlet KOT print issues | FX POS | FX POS | Bill Print | Swarnalatha Bairava Mohan | Production Issue | High | Completed | 2026-06-01 | 2026-06-05 | 30 | 22 | 100% | 5 | Jun-2026 | No | No | Yes | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 474
Internal | Internal | Whatspp POS Invoice Via Laison exe(API/proc) | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | New Requirement | Medium | Completed | 2026-06-05 | 2026-06-08 | 20 | 17 | 100% | 4 | Jun-2026 | No | No | Yes | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 475
Internal | Internal | Whatspp POS Invoice Via Laison exe (Exe changes) | FX POS | FX POS | Bill Print | Swarnalatha Bairava Mohan | New Requirement | Medium | Completed | 2026-06-08 | 2026-06-10 | 8 | 5 | 100% | 3 | Jun-2026 | No | No | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 476
1372718 | The Dukes Retreat; Khandala | Enable cash settlement /Receipt >=200000 | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | New Requirement | Medium | Completed | 2026-06-10 | 2026-06-16 | 30 | 20 | 100% | 7 | Jun-2026 | No | No | Yes | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 477
NA | TLG Portugal | TLG Changes Online and Offline | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | New Requirement | High | Completed | 2026-06-16 | 2026-06-20 | 30 | 10 | 100% | 5 | Jun-2026 | No | No | Yes | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 478
1361167 | Karan Sharq Hotel Apartments Co; | All E-Invoice log in One screen(All Operational module FOM,POS,SNC etc) | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | New Requirement | Medium | Completed | 2026-06-22 | 2026-06-25 | 10 | 5 | 100% | 4 | Jun-2026 | No | No | Yes | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 479
Internal | Internal | Migration Related changes For EXE and FX service | FX POS | FX POS | Bill Print | Swarnalatha Bairava Mohan | Internal Task | Medium | Completed | 2026-06-26 | 2026-06-30 | 30 | 10 | 100% | 5 | Jun-2026 | No | No | No | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 480
NA | Brigade Group | Offine -Fortune Next CMS to FX POS and FX SNC Integration | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | New Requirement | High | Completed | 2026-06-26 | 2026-06-30 | 15 | 15 | 100% | 5 | Jun-2026 | No | No | Yes | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 481
Internal | Internal | FX Steward app session selection LIVE issue fixing | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Production Issue | Critical | Completed | 2026-06-08 | 2026-06-15 | 48 | 44 | 100% | 8 | Jun-2026 | No | Yes | Yes | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 482
Internal | Internal | FX/FN Steward App Add received amount and balance amount to all payment modes | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-06-16 | 2026-06-19 | 32 | 36 | 100% | 4 | Jun-2026 | No | Yes | Yes |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 483
Internal | Internal | Add received amount and balance amount to all payment modes dev testing | FX POS | FX POS | Settlement | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-06-19 | 2026-07-19 | 4 | 4 | 100% | 1 | Jun-2026 | No | Yes | Yes |  | 4
Internal | Internal | FN Steward App Bill print not happening LIVE issue fixing | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Production Issue | High | Completed | 2026-06-22 | 2026-06-22 | 8 | 8 | 100% | 1 | Jun-2026 | No | Yes | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 484
Internal | Internal | Code and project architecture modifications for Auth flow | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Internal Task | Medium | Completed | 2026-06-23 | 2026-06-24 | 16 | 16 | 100% | 2 | Jun-2026 | No | Yes | No | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 485
Internal | Internal | FX/FN Steward App Add default amount for modifier amount | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-06-25 | 2026-06-25 | 6 | 4 | 100% | 1 | Jun-2026 | No | Yes | Yes | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 486
Internal | Internal | FX/FN Steward App KOT amend API response changes | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Internal Issue | Medium | Completed | 2026-06-26 | 2026-06-26 | 8 | 6 | 100% | 1 | Jun-2026 | No | Yes | No | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 487
Internal | Internal | FX/FN Steward App Searched menu items are not adding to the cart in one property | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Production Issue | High | Completed | 2026-06-29 | 2026-06-29 | 8 | 8 | 100% | 1 | Jun-2026 | No | Yes | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 488
Internal | Internal | FX/FN Steward App Settlement modes are arranged according to the classification name | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | Medium | Completed | 2026-06-30 | 2026-06-30 | 8 | 7 | 100% | 1 | Jun-2026 | No | Yes | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 489
NA | Global | POS UI upgrade to latest angular version | FX POS | FX POS | Order Entry | Lakmali Vithanalage | New Requirement | Medium | In progress | 2026-06-18 | 2026-07-17 | 200 | 100 | 80% | 30 | Jun-2026 | Yes | No | Yes | 40 | 86.7 | 113.3 | 0 | 0 | 0 | 0 | 0 | 1 | 491
NA | Club M Group | Spa -settlement copy,resettle remarks | FX POS | FX SPA | Billing | Devana Jagadeesh | New Requirement | High | Completed | 2026-06-29 | 2026-06-29 | 8 | 6 | 100% | 1 | Jun-2026 | No | Yes | Yes | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 549
1397935 | Riviera Hotel, Lagos | some cases happy hour item amount is writing in percentage column becasue of the there is improper bill amount showing on the bill. | FX POS | FX POS | Bill Print | Jhansi Nadella | Production Issue | Medium | QA-Staging | 2026-07-20 | 2026-07-21 | 16 | 10 | 50% | 2 | Jul-2026 | No | No | Yes | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 563
Internal | Internal | Nc percentage for menu wise for open item-API changes | FX POS | FX POS | Order Entry | Jhansi Nadella | New Requirement | Medium | QA-WIP | 2026-07-21 | 2026-07-21 | 8 | 8 | 50% | 1 | Jul-2026 | No | No | Yes | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 564
Internal | Internal | Nc percentage for menu wise for open item-UI changes | FX POS | FX POS | Order Entry | Rashmi Kumari | New Requirement | Medium | QA-WIP | 2026-07-21 | 2026-07-21 | 8 | 8 | 50% | 1 | Jul-2026 | No | No | Yes | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 565
Internal | Internal | Outlet type laundry should not show on POS App | FX POS | FX POS | Order Entry | Rashmi Kumari | Internal Issue | Medium | QA-Staging | 2026-07-20 | 2026-07-21 | 16 | 10 | 100% | 2 | Jul-2026 | No | No | No | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 566
1346644 | Sentrim Amboseli Lodge; Kenya | Integration with Kopo kopo Gateway-UI | FX POS | FX POS | Settlement | Lakmali Vithanalage | New Requirement | High | QA-WIP | 2026-07-20 | 2026-07-21 | 16 | 16 | 70% | 2 | Jul-2026 | No | No | Yes | 5 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 571
1415050 | The Dukes Retreat; Khandala | In Setup Service Master Require Download all and Search Filter option | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | Production Issue | High | In Progress | 2026-07-14 | 2026-07-21 | 48 | 40 | 70% | 8 | Jul-2026 | No | No | Yes | 14 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 1 | 572
1415052 | The Dukes Retreat; Khandala | Restrict duplicate items in Service Master | FX POS | FX POS | Order Entry | Swarnalatha Bairava Mohan | Production Issue | High | In Progress | 2026-07-14 | 2026-07-21 | 48 | 40 | 90% | 8 | Jul-2026 | No | No | Yes | 5 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 1 | 573
1416029 | Water Edge Srilanka | NC Report to add Staff name | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | High | QA-WIP | 2026-07-16 | 2026-07-17 | 16 | 16 | 90% | 2 | Jul-2026 | No | No | Yes | 2 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 582
Internal | Internal | Advance report in POS sales 7 reports | FX POS | FX POS | Reports | Sumanth Syam Kantipalli | New Requirement | Medium | QA-WIP | 2026-07-13 | 2026-07-16 | 32 | 30 | 50% | 4 | Jul-2026 | No | No | Yes | 16 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 591
NA | TLG Portugal | Revenue discount and tax exemption. Guest Exemption in FO | FX POS | FX POS | Order Entry | Jhansi Nadella | New Requirement | High | In Progress | 2026-07-22 | 2026-07-31 | 32 | 20 | 35% | 10 | Jul-2026 | No | No | Yes | 21 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 594
Internal | Internal | FX Steward App check user session active or not API implementation & dev test | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | High | Completed | 2026-07-21 | 2026-07-21 | 8 | 8 | 100% | 1 | Jul-2026 | No | Yes | Yes | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 627
Internal | Internal | FX Steward App clear user session UI's and API implementation & dev test | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | High | Completed | 2026-07-22 | 2026-07-23 | 16 | 16 | 100% | 2 | Jul-2026 | No | Yes | Yes | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 628
Internal | Internal | FX Steward App all logout APIs implementation | FX POS | FX POS | Order Entry | Wageesha Chinthaka | New Requirement | High | In Progress | 2026-07-23 | 2026-07-24 | 16 | 16 | 50% | 2 | Jul-2026 | No | #REF! | Yes | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 629 | #REF!
Internal | Internal | Code and project architecture modifications for ordering | FX POS | FX POS | Order Entry | Wageesha Chinthaka | Tech Upgrade | Medium | Not Started | 2026-07-27 | 2026-07-28 | 12 |  | 0% | 2 | Jul-2026 | No | Yes | No | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 630